## Waterfall Timeline
Waterfall Project Timeline
Project timeline from Aug 31 to Sep 26, 2026
Category / Area | Task Description | Status | Deadline | WEEK 1 (Aug 31 - Sep 06) | [6 empty] | WEEK 2 (Sep 07 - Sep 13) | [6 empty] | WEEK 3 (Sep 14 - Sep 20) | [6 empty] | WEEK 4 (Sep 21 - Sep 26)
|  |  |  | 31-Aug | 01-Sep | 02-Sep | 03-Sep | 04-Sep | 05-Sep | 06-Sep | 07-Sep | 08-Sep | 09-Sep | 10-Sep | 11-Sep | 12-Sep | 13-Sep | 14-Sep | 15-Sep | 16-Sep | 17-Sep | 18-Sep | 19-Sep | 20-Sep | 21-Sep | 22-Sep | 23-Sep | 24-Sep | 25-Sep | 26-Sep
|  |  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Team Schedule & Recurring Milestones
All Team | Recurring Team Sync Meeting | Scheduled | Tue/Sat -> Mon/Wed | WEEK 1 (Aug 31 - Sep 06) 01-Sep Tue: Sync; WEEK 1 (Aug 31 - Sep 06) 05-Sep Sat: Sync; WEEK 2 (Sep 07 - Sep 13) 08-Sep Tue: Sync; WEEK 2 (Sep 07 - Sep 13) 12-Sep Sat: Sync; WEEK 3 (Sep 14 - Sep 20) 14-Sep Mon: Sync; WEEK 3 (Sep 14 - Sep 20) 16-Sep Wed: Sync
Milestone / Review | Mentor Audit | Scheduled | 20-Sep (Sun) | WEEK 3 (Sep 14 - Sep 20) 20-Sep Sun: Audit
Member 1: Hussain
Groups / Invites | Invite and join request | In Progress | 03-Sep (Thu) | WEEK 1 (Aug 31 - Sep 06) 01-Sep Tue: Start; WEEK 1 (Aug 31 - Sep 06) 03-Sep Thu: Due
Group Events | Group events | Not Started | 07-Sep (Mon) | WEEK 1 (Aug 31 - Sep 06) 06-Sep Sun: Start; WEEK 2 (Sep 07 - Sep 13) 07-Sep Mon: Due
Extra Features | Extra features | Not Started | 11-Sep (Fri) | WEEK 2 (Sep 07 - Sep 13) 09-Sep Wed: Start; WEEK 2 (Sep 07 - Sep 13) 11-Sep Fri: Due
UI / Frontend | UI | Not Started | 13-Sep (Sun) | WEEK 2 (Sep 07 - Sep 13) 13-Sep Sun: Due
UI / Frontend | UI | Not Started | 15-Sep (Tue) | WEEK 3 (Sep 14 - Sep 20) 15-Sep Tue: Due
QA / Testing and bug fixes | Testing and bug fixes | Recurring QA | 19-Sep (Sat) | WEEK 1 (Aug 31 - Sep 06) 04-Sep Fri: Test; WEEK 2 (Sep 07 - Sep 13) 11-Sep Fri: Test; WEEK 3 (Sep 14 - Sep 20) 17-Sep Thu: Test; WEEK 3 (Sep 14 - Sep 20) 18-Sep Fri: Test; WEEK 3 (Sep 14 - Sep 20) 19-Sep Sat: Test
Member 2: Ahmed
Posts / Feed | Post CRUD | In Progress | 03-Sep (Thu) | WEEK 1 (Aug 31 - Sep 06) 01-Sep Tue: Start; WEEK 1 (Aug 31 - Sep 06) 03-Sep Thu: Due
Posts | Post uploads and comments | Not Started | 07-Sep (Mon) | WEEK 1 (Aug 31 - Sep 06) 06-Sep Sun: Start; WEEK 2 (Sep 07 - Sep 13) 07-Sep Mon: Due
Group Posts | Group posts and comments | Not Started | 11-Sep (Fri) | WEEK 2 (Sep 07 - Sep 13) 09-Sep Wed: Start; WEEK 2 (Sep 07 - Sep 13) 11-Sep Fri: Due
UI / Frontend | Post UI | Not Started | 13-Sep (Sun) | WEEK 2 (Sep 07 - Sep 13) 13-Sep Sun: Due
UI / Frontend | Group post UI | Not Started | 15-Sep (Tue) | WEEK 3 (Sep 14 - Sep 20) 15-Sep Tue: Due
QA / Testing and bug fixes | Testing and bug fixes | Recurring QA | 19-Sep (Sat) | WEEK 1 (Aug 31 - Sep 06) 04-Sep Fri: Test; WEEK 2 (Sep 07 - Sep 13) 11-Sep Fri: Test; WEEK 3 (Sep 14 - Sep 20) 17-Sep Thu: Test; WEEK 3 (Sep 14 - Sep 20) 18-Sep Fri: Test; WEEK 3 (Sep 14 - Sep 20) 19-Sep Sat: Test
Member 3: Sayed
Profile | Profile Backend and CRUD and frontend | In Progress | 03-Sep (Thu) | WEEK 1 (Aug 31 - Sep 06) 01-Sep Tue: Start; WEEK 1 (Aug 31 - Sep 06) 03-Sep Thu: Due
Privacy & Followers | Privacy and following | Not Started | 07-Sep (Mon) | WEEK 1 (Aug 31 - Sep 06) 06-Sep Sun: Start; WEEK 2 (Sep 07 - Sep 13) 07-Sep Mon: Due
Profile & Stats | Follow requests and avatar and stats and post stats | Not Started | 11-Sep (Fri) | WEEK 2 (Sep 07 - Sep 13) 09-Sep Wed: Start; WEEK 2 (Sep 07 - Sep 13) 11-Sep Fri: Due
UI / Frontend | UI | Not Started | 13-Sep (Sun) | WEEK 2 (Sep 07 - Sep 13) 13-Sep Sun: Due
UI / Frontend | Avatar UI | Not Started | 15-Sep (Tue) | WEEK 3 (Sep 14 - Sep 20) 15-Sep Tue: Due
QA / Testing and bug fixes | Testing and bug fixes | Recurring QA | 19-Sep (Sat) | WEEK 1 (Aug 31 - Sep 06) 04-Sep Fri: Test; WEEK 2 (Sep 07 - Sep 13) 11-Sep Fri: Test; WEEK 3 (Sep 14 - Sep 20) 17-Sep Thu: Test; WEEK 3 (Sep 14 - Sep 20) 18-Sep Fri: Test; WEEK 3 (Sep 14 - Sep 20) 19-Sep Sat: Test
Member 4: Bader
WebSocket | WebSocket backend and frontend | In Progress | 03-Sep (Thu) | WEEK 1 (Aug 31 - Sep 06) 01-Sep Tue: Start; WEEK 1 (Aug 31 - Sep 06) 03-Sep Thu: Due
Chat / Messaging | Private chat and group chat | Not Started | 07-Sep (Mon) | WEEK 1 (Aug 31 - Sep 06) 06-Sep Sun: Start; WEEK 2 (Sep 07 - Sep 13) 07-Sep Mon: Due
Notifications | Notifications | Not Started | 11-Sep (Fri) | WEEK 2 (Sep 07 - Sep 13) 09-Sep Wed: Start; WEEK 2 (Sep 07 - Sep 13) 11-Sep Fri: Due
UI / Frontend | UI | Not Started | 13-Sep (Sun) | WEEK 2 (Sep 07 - Sep 13) 13-Sep Sun: Due
UI / Frontend | UI | Not Started | 15-Sep (Tue) | WEEK 3 (Sep 14 - Sep 20) 15-Sep Tue: Due
QA / Testing and bug fixes | Testing and bug fixes | Recurring QA | 19-Sep (Sat) | WEEK 1 (Aug 31 - Sep 06) 04-Sep Fri: Test; WEEK 2 (Sep 07 - Sep 13) 11-Sep Fri: Test; WEEK 3 (Sep 14 - Sep 20) 17-Sep Thu: Test; WEEK 3 (Sep 14 - Sep 20) 18-Sep Fri: Test; WEEK 3 (Sep 14 - Sep 20) 19-Sep Sat: Test

## Sheet1
Category / Area | Task Description | Status | Deadline
WebSocket | WebSocket backend and frontend | In Progress | 02-Sep (Thu)
| Notifications |  | 03-Sep (Thu)
Groups / Invites | Invite and join request | In Progress | 05-Sep (Sat)
Posts / Feed | Post CRUD | In Progress | 05-Sep (Sat)
Profile | Profile Backend and CRUD and frontend | In Progress | 05-Sep (Sat)
Group Events | Group events | Not Started | 05-Sep (Sat)
Posts | Post uploads and comments | Not Started | 07-Sep (Mon)
Privacy & Followers | Privacy and following | Not Started | 07-Sep (Mon)
| group chat |  | 07-Sep (Mon)
Chat / Messaging | Private chat | Not Started | 07-Sep (Mon)
Extra Features | Extra features | Not Started | 11-Sep (Fri)
Group Posts | Group posts and comments | Not Started | 09-Sep (Wed)
| Follow requests |  | 09-Sep (Wed)
| avatar setup |  | 09-Sep (Wed)
Profile & Stats | profile stats, post stats | Not Started | 09-Sep (Wed)
Notifications | Notifications | Not Started | 11-Sep (Fri)
UI / Frontend | UI | Not Started | 13-Sep (Sun)
UI / Frontend | Post UI | Not Started | 13-Sep (Sun)
UI / Frontend | UI | Not Started | 13-Sep (Sun)
UI / Frontend | UI | Not Started | 13-Sep (Sun)
UI / Frontend | UI | Not Started | 16-Sep (Wed)
UI / Frontend | Group post UI | Not Started | 16-Sep (Wed)
UI / Frontend | Avatar UI | Not Started | 16-Sep (Wed)
UI / Frontend | UI | Not Started | 16-Sep (Wed)
QA / Testing and bug fixes | Testing and bug fixes | Recurring QA | 19-Sep (Sat)
QA / Testing and bug fixes | Testing and bug fixes | Recurring QA | 19-Sep (Sat)
QA / Testing and bug fixes | Testing and bug fixes | Recurring QA | 19-Sep (Sat)
QA / Testing and bug fixes | Testing and bug fixes | Recurring QA | 19-Sep (Sat)
Milestone / Review | Submission | Scheduled | 20-Sep (Sun)
All Team | Recurring Team Sync Meeting | Scheduled | Tue/Sat -> Mon/Wed